DAQ: Status of Upgrade / Tasks
Outline
Overview of DAQ Upgrade
  - Motivation
  - Architecture
  - Projects / People
  - Hardware: Readout and IPU-boards
    - TRB V1, Dev-Board (HadCom), TRB V2
    - TOF-Readout/IPU, MDC-Readout/IPU
    - Trigger Distribution / TRB-Network
EU-Contract and BMBF money
Discussion
  - Tasks for participants
  - Schedule / Estimates

---
Motivation: bad performance!
DAQ performance not sufficient for large systems
  - LVL1 and LVL2 transfer
LVL2 trigger not efficient (high reduction rate) anymore
maintenance
  - zoo of hardware is hard to handle
  - decaying and obsolete components
  - does not scale easily (Trigger-Bus/Hub, MU)
    - how to integrate the RPC detector

---
Mission Statement
List of Projects for DAQ upgrade
Objective: 20 kHz primary data rate to ensure measuring rare decays in heavy systems

---
Architecture of new DAQ

---
Projects: Boards and Software
RPC-Readout: TRB V1	[done]
ETRAX_DEV1 / HadCom	[done]
TRB V2	[layout finished]
GP-Add-On	[schematics]
MDC Add-On	[schematics]
RICH-Add-On	[will start soon?]
MDC driver card	[open topic]
EventBuilder Software	[work started]
RICH-Ring-finder (higher reduc.)	[work started]
LVL2 Trigger Algorithm (Meta)	[??]
TrbNet (Trigger and IPU Net)	[work started]
MDC cluster search algo.	[??]
TOF-wall FEE (TOT)	[FEE concept ready, ???]
MU V2	[Basic functionality tested]
....

---
Involved People I
Ingo Fröhlich
  - TRB-Network, TOF-Readout and IPU, Hardware-design
Marek Pałka
  - TRB V1, DEV-Board (2 GBit/s Links), TRB V2 (FPGA for readout)
Radek Trebacz
  - Programming of ETRAX-Processor and Co-Processor (DAQ-readout)
Attilio Tarantola
  - MDC-readout and MDC-IPU
Marcin Kajetanowicz
  - Hardware design and schematics

---
Involved People II
Sergey Yurevich
  - DAQ-Software (EventBuilder upgrade)
  - RICH-IPU Algorithm, VHDL?
Christoph Schrader
  - learning, TRB-Network, ...
Michael Traxler
  - Hardware-Design, Coordination
Michael Böhmer
  - RICH-Readout, IPU
Peter Skott
  - Layout

---
Architecture TRB1, just readout
DC/DC
48V
TRB V1.0
TDC
32
channels
Computer +
Memory +
Flash +
Network
FPGA
FIFO
Dual Ported RAM
TDC
32
channels
TDC
32
channels
TDC
32
channels
Ethernet
Triggerbus

---
TRB Module and components
4*32 channels TDC, HPTDC
80 pin twisted pair cable, KEL connector
Single Chip Computer with Ethernet
FPGA
DC/DC 48V, isolated
Memory

---
Results for TRBv1
Performance:
  - LVL1 readout of 60 TDC-words/event: 35kHz
  - LVL1 readout: only header and trailer: 80kHz
  - LVL2 readout of 60 words/event: 5-6kHz
  - LVL2 readout of empty events: 18-19kHz
  - all without DMA, no optimization in FPGA
TDC-Resolution
  - sigma between 2 channels (4 TDCs): 38ps
  - no signs of crosstalk on TRB (has to be verified with more careful measurement)
  - RPC-detector channel resolution: 80ps

---
TRB V2 Block Diagram
TRB V2.0
TDC
32
channels
TDC
32
channels
TDC
32
channels
TDC
32
channels
FPGA
Virtex 4
LX40-200
(1148 pins)
DSP /
Tiger SHARC
Trigger and
IPU data
over optical
 link
Computer +
Memory +
Flash +
Network
Connector to
Add-On
board
Ethernet

---
ETRAX_FS_DEV1 / HadCom
on the way to TRBv2
Purpose:
  - Validate ETRAX-FS (3 I/O-Co-Processors)
  - Translate between old-Trigger-bus and new optical trigger-bus
  - Connectivity to Concurrent-VME-CPU (Acromag)
Status:
10 assembled boards available (5 with 2 flash-chips)
Booting of Linux, Flash-Boot working now
2 times 2 Gbit/s Optical Links are working without errors for 3 days (50m cable, Marek)
Driver / Code for Co-Processor worked on in Krakow and GSI (Radek and Attilio)
ready for TRBv2

---
Status I, ETRAX-FS-DEV1 and Trigger-converter

---
TRBv2, status
schematics grown with experience of HadCom
layout almost finished
PCB available in mid-November
Assembly finished: beg. December
TRBv1 functionality: July 2007
Full featured: beg. 2008

---
TOF readout / concept / status
Concurrent VME-CPU + Acromag PCI card + HadCom
intermediate step: TOF-FEE could be TRB compatible
Concurrent CPU + Acromag card: „hello world“
HadCom: ready to be used
VME-CPU can be upgraded easily
Time estimate / priority ?

---
MDC-readout / TRBv2 Add-On Board / concept / status
Concept:
Replacement of:
  - mini-VME-crate
    - RC, Concentrator, TriggerModule
  - readout VME-crate
    - DTU, SAMs, VME-CPU
with: TRBv2 Add-On-board
Status: (Attilio)
Schematics: 95%
MDC-Test-Setup: not ready
State-Machines (paper): done
Future:
MDC-Driver Cards

---
TRB-Net / Trigger-IPU-Network
One common data and trigger transport „library“ for all subsystems
  - problems are solved only once for all systems
Flexible Communication Protocol
  - Low latency for Trigger-Purposes
  - Stream mode for IPU data
  - 16 channels for sharing one medium
Ingo
  - status / time-estimate / needed support
Trigger-Hub
  - 10 (15) inputs / 1 output
  - FPGA-LatticeSC (16 times 3-Gbit/s-Serdes)
  - schematics will be started soon: Add-On to TRBv2 ?

---
Other boards / tasks
General Purpose Add-On-board
  - Schematics finished
  - TRBv2 connection to Acromag + old TriggerBus (Hub)
RICH Ring online finder: (Sergey)
  - surveying data, already ideas?
RICH readout and RICH-IPU
  - TRB Add-On
  - Serial communication from RICH-FEE-backplanes to RICH-Readout
  - Michael B.
    - ideas / commitment / time estimate

---
Central Trigger System (CTS) in a “mixed mode”

---
Unsolved problems / no commitment
Manpower for VULOM (VME-Universal-Logic-Module)?
TOF-FEE (TOT-measurement): Any commitment?
  - the concept is similar to the Forward-Wall FEE
MDC-cluster search online algorithm
  - occupancy in MDC for Au+Au ?
LVL2 Trigger Algorithm in Meta
  - Matching Window optimization ?
  - occupancy in meta for Au+Au ?
if LVL2 fails: LVL2 data rate must be high enough to take everything....
things I forgot ....

---
EU-Contract / Money:
Where we are now?
Money spent (invest) by me on the account of others in 12 month (2005-10-01 till 2006-10-01):
cost estimate:
  - RPC: 30 times TRBv2: 30 x 1.6k€ + 2k€ offset	= 50k€
  - Hubs: 10 x 700€ + 2000€ offset	= 9k€
  - GP-Add-On: 5 x 400€ + 1000€	= 3k€
  - Accessories:	= 10k€

---
Let's do things better...
Mission Statement
Things to learn from HADES-experiences:
Don't allow a zoo of digital-hardware for every subsystem
Think in modules rather than boards
  - team members work on modules not on boards
  - teams work together to get the whole system running rather than their board (who is guilty: MDC or RICH?)
Data transport issues are at least 10 times more demanding / time-consuming than the algorithm to implement (maybe connected to the zoo of hardware)
Think more about Low-Voltage Power-Distribution

---
more things?
Discussion

---
Time schedule