HADES Data Acquisition Upgrade Overview and Status
Outline
Motivation / Aim
DAQ-Projects
  - TRB, RPC, MDC, TOF, RICH,Shower, TRB-Net, CTS
  - Status / Manpower involved / schedule / risk
Summary

---
Motivation / Aim
Main Problem:
  - The limitation of the LVL1/LVL2 rate
Measures:
  - Increase LVL1/LVL2-rate capability
  - Improve on the LVL2 trigger-algorithm (W. Kühn)
Objective: 20 kHz primary data rate to ensure measuring rare decays in heavy systems
Risk: Not finished till August 2008 (+ 6 months comm.)

---
Consequences: Subsystems to be modified / exchanged
„Everything“ has to be touched / replaced
One common platform:
  - easier to debug, distributed knowledge, less maintenance, lower cost
  - stable!
  - usable for others: PANDA (2 groups), CBM, Coimbra (PET), KVI, etc.

---
“new” DAQ Architecture
Frondend Readout,
e.g. RPC-TRB
Frondend Readout,
e.g. RPC-TRB
Frontend Readout,
e.g. RPC-TRB
Fut,
e.g. MDC-TRB
Frondeout,
e.g. MDC-TRB
Frontend Readout,
e.g. MDC-TRB
.....
Eventbuilders
Ethernetswitch
Ethernet Switches
Ethernet: data / slow control
Compute-Node +
Trigger-Link-Hub
Compute-Node +
Trigger-Link-Hub
.....
Optical GB-Link
Central Trigger System
Trigger Box
Matching Unit
CTU
Trigger and IPU-data
Eventbuilders
Eventbuilders
(10)

---
TRBv2 [1]: Status
All features we need are included
successfully used for the RPC-beam time, stable!
Still missing:
  - DSP application
  - DMA on CPU
[1] “A new Trigger and Readout Board for HADES and FAIR experiments”, IEEE Trans. Nucl. Sci, accepted

---
Status / Manpower / Schedule
TRB Network + HUB
Purpose:
distribute triggers, IPU-data, data transport, slow-control
TRBv2-AddOn: FPGA with 16x 2GBit/s optical links
Status:
optical links: working
TRB-Network for point to point connections is finished
Schedule:
TRB HUB VHDL-code: Ingo Fröhlich, Jan Michel: 4 months

---
MDC Setup: current and new (with TRB)

---
Status / Manpower / Schedule / Risk
TRB-MDC-Add-on
Readout of MDC-Motherboards
Manpower: Attilio Tarantola
Readout on TRB: the same as for HPTDC
Status: can read 2 chains of motherboards
Risk: very low
nearly finished project

---
Status / Manpower / Schedule / Risk
TRB-MDC-Driver-cards
Strong demand for new MDC-driver cards:
  - cables! cables! cables!
    - crosstalk and "ringing" of the MDC-FEE due to copper cables squeezed between motherboards
    - etc.
Project: New MDC-driver card
  - Optical Transmission via Polymere Optical Fibre (POF)
  - FPGA (SERDES) on driver card for data-transmission
  - Timing-signal via a small differential copper cable

---
Status / Manpower / Schedule
TRB-MDC-Driver-cards II
Status
PCB is assembled, ready to be tested
Schedule:
Readout-Controller code is finished
communication: 6 months
Manpower:
Attilio Tarantola + NN

---
Status / Manpower / Schedule / Risk
TOF-detector-FEE
FEE with Q2W logic needed for TRB
  - rest: identical to RPC
  - remove CAMAC etc.
Evgueni Usenko
  - Analogue expert, NINO ASIC
Concept:
  - TRB-add-on with PM-amplifier and
    Q2W logic for 64 channels, based on
    the NINO-ASIC
Status / Schedule:
PCB ordered
evaluation of prototype till February 2007
Risk: technically: low (fallback: Forward-Wall electronics / VME-based readout)

---
RICH-FEE + RICH-DAQ Replacement
Goals:
  - Higher bandwidth
  - less noise
  - higher sensitivity
    - lowering high-voltage
Consequences
  - New frontend (new pre-amp)
  - ADC-module
  - Readout by TRB + AddOn (TRB-HUB-AddOn)

---
RICH DAQ-Upgrade: Status
Prototype PCB for APV25 is working for R3B in beam
  - data needs still some analysis
components available (APV25)
design and PCB-layout of ADC-module is finished

---
Status / Manpower / Schedule / Risk
RICH-DAQ-upgrade
Schedule:
2nd generation FEE will be tested in January 2008
ADC-Module available end of this year
Manpower:
Michael Böhmer
new: Ludwig Maier + Michael Weber + probably a student

---
Status / Manpower / Schedule / Risk
Shower-DAQ-upgrade
Concept:
TRBv2-Add-on replaces „Readout-Boards“ + VME-readout + Fanout-board
Status:
Schematics finished, in PCB-layout queue
Schedule:
PCB in December, working prototype in February
Manpower:
Marcin Kajetanowicz
Risk:
Low, fallback: current system (shower is our fastest system!)

---
DAQ-Software: Event-Building + Run-Control
DAQ-software:
Parallel Eventbuilding: 10 event-builder PCs
  - data is sent from the sources to different event-builders
Run-Control: control 100 boards instead of 10, 1000 FEE-boards
Status:
Many sources with different queue-sizes can be handled
script-based run-control is existing

---
LVL1 Trigger / Trigger Box / VULOM / CTS
Consolidate the LVL1 Trigger
  - one module: “VULOM3”
  - replaces Trigger-Box and has additional features
Davide Leoni (since March 2007)
  - tested in beam!

---
More DAQ-projects
Slow-Control:
  - EPICS infrastructure: EE-department (P. Zumbruch)
  - Monitoring
  - Thresholds and other settings / readings through TRB
    - for RPC this is done by: Elena Castro and Alex Gil

---
Summary
Large and demanding project!
progress: looks very promising
some things with still open issues (no show stoppers known!)
Finished hard/software: August 2008
Finished commissioning: February 2009
„Future-DAQ“ is happening now at HADES and it is getting exciting as the integration comes soon!
Many people involved!

---
Summary: DAQ-Upgrade: People

---
DAQ upgrade
Thank you for your attention!

---
RICH Realtime-Schedule
New PCB-designs: 1 month, til 1. Feb.
Production: 1 Month: 1. March
- "Final" Test-Setup (1 Sector in Munich) assembled: 1. April
- Final Tests on one sector: 1 month: 1. May
- June: Decision, if new RICH-FEE-DAQ-solution is what we want
If positive:
- Mass production for whole RICH-detector: 3 months: 1. September
- Mechanical replacement at GSI-RICH: 2 month: 1. November
- Commissioning: 3 month: til 1. Feb. 2009
- Architechture discussion / component availability
Finished: End of April 2007
- Prototype system: AFE-ADC-BP(1)-LM
Schematics: 1. July
PCB-design: 1. August
Assembled boards: 1. September
During production time: VHDL-code development
Function / Performance Tests: 4 Month, til 1. Jan 2008
During tests: new schematics

---
TOF-FEE upgrade
- Architechture discussion / basic investigations Finished: 15.04.07
- Prototype system: Full featured TRBv2 Addon-board
Schematics: finished <30.04 - 15.05.07>
PCB-design: <duration 15.05 - 15.06.07, finish-date 15.06.07>
Assembled boards: <duration PCB prod. 15.06 - 1.07.07, finish-date ass. board 15.07.07>
During production time: VHDL-code development of the DAQ-group, (no comment)
Function / Performance Tests: <duration 15.07 - 30.07.07, date>
During tests: new schematics are prepared
- New PCB-designs: 1 month, < 1.08 - 30.08.07>
Production: 2 Month: < 1.09 - 30.09.07> note: 1 Month
- "Final" Test-Setup assembled: < 1.10 - 15.10.07>
- Final Tests on one sector: < 15.10 - 15.11.07>
- Decision, if new TOF-FEE-DAQ-solution is what we want
If positive:
- Mass production for whole TOF-detector: 3 months: < 5.01 - 1.03.08>
- Mechanical replacement at HADES-TOF: < from 1.03.08>
(this has to be done by the TOF-people!)
- Commissioning: 3 month: middle of 2008 year

---
Backup-Solution
If we will not have a LVL2 trigger for Au+Au we can expect (worst case):
  - 150 MBytes/s sustained rate (300 MBytes/s peak)
This is very inconvenient:
  - 86 TBytes / week
  - expensive (8k€ for tapes/week)
  - Compression can save 30% (tested)
DAQ and IT-department are able to do this
Comparison:
  - Phenix is writing since 2004 350MBytes/s sustained to tape (600MBytes/s with compression).

---
LVDS
TTL
TTL
Virtex4
(LX40)
Etrax-FS
SDRAM
2GBit/s
optical link
DSP
(TS201)
HPTDC
HPTDC
HPTDC
HPTDC
Optional
SDRAM
Add-on connector
100MBit/s
Ethernet

---
TRB V2, why? consequences?
Advantages to use TRB V2 as DAQ-FEE-system
Use one common platform for all subsystems!
  - Concentrate manpower on one main project
    - data transport issues are solved only once => more stable
    - easier to debug, distributed knowledge, less maintenance, lower cost
Interesting also for other experiments: CBM, Panda, PET-readout
Nothing is for free, general solution needs...
  - more time until deployment (more complex)
  - new trigger / IPU-bus over optical links (IP-core)
  - many people involved, more communication, better documentation needed, ... => advantage